## Slide 1
Ian Pong (ipong@lbl.gov)
on behalf of the SMP Materials Team
Lawrence Berkeley National Laboratory
HTS Cable Test Facility Project - Conductor Status

## Slide 2: Outline
Status (scope and schedule)
  Wire procurement
  Bare cable fabrication
  Direct braiding
With contributions from Al Baskys, Jean-Francois Croteau, Elizabeth Lee, Andy Lin, and Michael Naus
Wire
Cable
Braiding

## Slide 3: Status: Wire Procurement
Wire for the Development Cables (completed)
  LBNL PO 7509895 – 108/127 RRP® in Cable W10OL1301
  CERN DEM-1.1 Wire – 162/169 RRP® in Cable W12OL1302
Prototype (completed)
  LBNL PO 7576493 – 162/169 RRP® in Cable W12OL1303
Production (in progress)
  LBNL PO 7629842 – 162/169 RRP® for 5 cables (3 long, 2 short)
  Signed on 2022 03 11
  Shipment A due ~2022 09
  Last shipment by 2022 06 01
Expecting to buy an extra unit as spare
Photo credit: Al Baskys
Wire
Cable
Braiding

## Slide 4: Status: Bare Cable Fabrication
Development Cables (completed)
  A paper published: https://doi.org/10.1109/TASC.2021.3094410
Prototype Cable (completed)
  A special seminar: W12OL1303 Cable Summary Presentation 2022 05 18
Production Cables (to start in spring 2023)
  Hardware upgrades in progress
  Diagnostics upgrades in progress
  Possibly preceded by a dummy (Cu) cable to qualify upgrades and minimize risk (threat)
Wire
Cable
Braiding
Photo credit: Al Baskys and Jean-Francois Croteau

## Slide 5: The Prototype Cable Observations
Payout direction
155 mm
72.4 mm
81.5 mm
25.86 mm
19.7°
17.6°
Top face
Bottom face
The twist pitch on the top face is significantly shorter leading making it less compact and resulting in gaps
The top roller likely running at different speed relative to the cable than the bottom roller
Mandrel asymmetry during run also indicates that cable biased towards the top roller
Wire
Cable
Braiding

## Slide 6: Alignment and Asymmetry
After 1303 cable production run, vertical misalignment of the mandrel and cable axes observed
Misalignment likely caused
  Asymmetric mandrel angle for the top and bottom broad faces
  Asymmetric friction and possibly thereby different relative speed wrt rollers
Suspected cause for strand gap on top cable face
0.5 mm
1.5 mm
Roller aperture
Mandrel tip
Wire
Cable
Braiding

## Slide 7: Good news: Extracted Strand RRR is good
Cable ID | Wire ID | Major RRR | Minor RRR | Bottom RRR | Top RRR | End-to-End
W12OL13037A05E | WO11S20517A01A | 140 | 195 | 251 | 224 | 223
W12OL13037A11E | WO11S20506A05A | 179 | 271 | 321 | 281 | 285
W12OL13037A16E | WO11S20506A03A | 133 | 214 | 271 | 233 | 234
W12OL13037A21E | WO11S20517A02A | 162 | 251 | 318 | 268 | 274
W12OL13037A27E | WO11S20517A02A | 186 | 252 | 323 | 263 | 277
W12OL13037A33E | WO11S20515A01A | 162 | 235 | 325 | 266 | 273
W12OL13037A38E | WO11S20515A01A | 171 | 258 | 329 | 277 | 283
W12OL13037A43E | WO11S20516A01A | 120 | 159 | 194 | 159 | 169
Extracted Strad Average |  | 157 | 229 | 292 | 246 | 252
Strand from billet #20516 worse than others, consistent with vendor and start-up RRR data
Specification: >100
Wire
Cable
Braiding

## Slide 8: Nevertheless: Cabling Machine Improvements
Diagnostics (in progress)
  Monitoring and logging motor/roller speed as well as motor voltage for any indications of motor load/speed imbalance
  Monitoring lubricant rate
  Monitoring slip on caterpuller
  Ambient conditions during cabling runs
  …
Turkshead (in progress)
  Higher power motors with drivetrain modification
  Encoders for semi-closed loop control and single point safety stop
  …
Wire
Cable
Braiding
Photo credit: Elizabeth Lee

## Slide 9: Status: Direct Braiding
Prototype Cable (completed)
  LBNL PO 7631056 – also procured sufficient raw material for the production cable
Production Cable
  Need 10-stack hardware upgrade: Web Job Order #J28098.B
Wire
Cable
Braiding