## Slide 1: G. Sabbi, LBNL Integrated Project Team meeting #7 January 20, 2023
TFD Status

## Slide 2: Presentation Outline
Budget Updates
  Procurement quotes vs. allocated budget
  Testing at Fermilab
  Magnet fabrication effort
Schedule Update
  Comparison IPT7 vs. IPT6
Engineering Design and Documentation
Test facility interfaces
Summary

## Slide 3: Magnet Design
D. Arbelaez, P. Ferracin, R. Hafalia, P. Mallon, D. Martins Araujo, J. L. Rudeiros Fernandez, G. Vallone et al.
Parameter | Unit | Value
Shell OD | m | 1.3
Shell length | m | 2.0
Total length | m | 2.9
44 turns/layer
40 turns/layer

## Slide 4: Vendor Quotes/Estimates

## Slide 5: Summary and Budget Update
Wire: +164k$
Cable insulation: -74k$
Coil tooling: -179k$
Coil parts: -106k$
Structure: +224k$
Total: -30k$
Updated 12/9/2022

## Slide 6: Magnet Test at Fermilab
FNAL test scope:
Cool down with dummy coils
  effort may be covered by facility commissioning funds
Two vertical tests: Fermilab provided estimate based on agreed requirements

## Slide 7: Magnet Test at Fermilab
Reference: TFT_Test-PAMS Budget-TFT _Test_at_HFVMTF-FY23
Summary
Included:
Cold test with TC
Setup
TC1: 2.5 wks
TC2: 1 wk
15-20 quenches
Basic analysis
Total requested (k$):
Labor: 142.4
M&S: 81.8
Total: 210.8
Previous (EOC2) budget:
  Test 1: 198.8 k$ (w/TC)
  Test 2: 173.3 k$ (no TC)
Budget was revised to reflect FNAL estimate
Detailed analysis covered separately
Need to add contingency

## Slide 8: Magnet fabrication effort
Updated “bottom up” effort estimate by engineering team is consistent with TFD budget allocations

## Slide 9: TFD Schedule: IPT7 vs. IPT6
August 2022 (EOC2/IPT6)
January 2023 (IPT7)
+4 months

## Slide 10: Design, Prototype Cable and Coil

## Slide 11: Production Cables and Coils

## Slide 12: Structure, Assembly and Test

## Slide 13: Funding Profile

## Slide 14: Engineering Design and Documentation
Continued work to implement full CAD model and fabrication drawings
  End plates, laminated structures, insulation schemes, impregnation surfaces

## Slide 15: Test Facility Interfaces and Specifications
Interface document to defined agreed upon parameters and capture additional details or changes
  Example: final coil length, magnet dimensions and weight were provided in November 2022 – about 10% additional margin for sample holder design, magnet mechanical support, quench protection etc.
  Under discussion: use of CLIQ for protection
Evolve in a formal agreement as both magnet and facility design are finalized

## Slide 16: Summary
Main updates from IPT6:
Continued work with vendors and LBNL/FNAL team to reconfirm procurement and effort estimates for magnet fabrication and testing – overall there are no significant changes to allocated budget
Following a successful Wire Specification Review we requested a final quote for the production wire and placed the order. First production batch (about 1.5 coil worth) was completed and accepted
Design and analysis effort has focused on incorporating engineering requirements and fabrication/assembly considerations, including feedback from vendors on component manufacturability and cost
Engineering design has been slipping, resulting in additional 4 months delay on project completion
Additional work is also needed in preparation for cable production runs
Availability of resources/infrastructure for engineering design and magnet fabrication is a challenge

## Slide 17: Additional Slides

## Slide 18: Risk Register

## Slide 19: Risk Register

## Slide 20: Preliminary drawings for vendor feedback
Al. Shell
End plate (lead end)
Winding pole (coil 1, middle)
Axial Rod
Base Plate (middle)
Winding pole (coil 1, end)
Coil end shoe
Iron yoke
Wedge
Base Plate (end)

## Slide 21: Fabrication infrastructure
Completed reaction furnace relocation to new building 77 addition
  Recommissioning tests planned for September.
The impregnation chamber has been moved to its new location in B77-103.
  Vacuum test completed, seismic anchoring in progress.
Winding table upgraded based on FE analysis for large TFD coils

## Slide 22: Funding Profile – IPT6
Next 3 quarters: 2.4 M$
M&S: 1.4 M$ (coil tooling/parts & structure)
Labor: 1M$ (prototype coil, production cables)

## Slide 23: Design, Prototype Cable and Coil (IPT6)

## Slide 24: Production Cables and Coils – IPT6

## Slide 25: Structure, Assembly and Test – IPT6